## Sheet1
Bug | Title | Expected Result | Actual Result | Link | Status | Notes
1 | User can skip mandatory fields in the Edit screen without alert or validation | The system should validate all mandatory fields. If any required field is empty, an alert message should be displayed preventing submission. The user should not be able to save or proceed until all required fields are correctly filled. | The system allows editing without filling mandatory fields. No alert messages are displayed, leading to incomplete or invalid data being saved in edit process | https://www.screenpresso.com/=emGsk1DFNLrz | closed
2 | Unnecessary Fields Displayed in Page Screen | Only relevant and required fields should be displayed on the screen. Unnecessary fields should be hidden to avoid confusion and improve user experience. | Fields that are not needed or not used in the process are still being displayed. This causes clutter and may confuse users or lead to incorrect data entry. | https://www.screenpresso.com/=3v6ATFqjhNJt | closed
3 | Add Descriptions, Examples, or Info Icons to Form Fields for Better Usability | Fields should have tooltips, examples, or short descriptions under the label. Alternatively, an info icon next to the label (🛈) that shows helpful text on hover or click. Users should clearly understand what each field expects. | Field labels are too generic or unclear . No descriptions, no tooltips, and no examples are provided. This results in confusion, especially for new users or less technical users. | https://www.screenpresso.com/=Pg8aEl9jWFwe | closed
4 | Missing Asterisk (*) Next to Mandatory Fields | All required (mandatory) fields should include a red asterisk * next to the field label (e.g., URL *). This helps users quickly identify which fields must be filled before submitting. | Required fields do not have a visual indicator (asterisk). Users may skip these fields unintentionally, resulting in validation errors upon submission. | https://www.screenpresso.com/=3VRPRv82jNfz | closed
5 | System accept duplicate same data or create new page with same data created before that case 2 pages have same data in created system | The system should prevent creating duplicate pages with the same data. A clear validation message should appear: "A page with the same title/content already exists." Alternatively, the system should update the existing page (if that's the expected logic). | The system allows creating two or more identical pages with the same title and data. No error or warning is shown. The duplicate appears in the page list, causing confusion. | https://www.screenpresso.com/=pa1PMwZIN5Vt | open | Discusstion
6 | Need Direct Button to Navigate to System URL After Creation (Not Only via Localhost or Manual Copy-Paste) | A direct clickable button should be provided after system creation or deployment to open the actual hosted URL (e.g., https://client-system.domain.com). This button should dynamically detect and use the server-assigned domain or public IP instead of localhost. The button could be labeled: 🔗 "Open System in New Tab" or "Go to Deployed System" | After creating or deploying a new system instance from the server, the system only displays the localhost URL (e.g., http://localhost:3000 or similar). Users are required to manually copy and paste or modify the URL to access the system via a real server/domain. |  | closed
7 | "Preview" Button Redirects to 'Page Not Found' not display any error details or guidance for resolving the issue. | If an error occurs, display a clear error message with details or logs that explain why the page could not be found | The redirected page shows a "Page Not Found" error. No information is given about the cause of the issue or how to resolve it. | https://jam.dev/c/c3640037-a5c9-4e5d-9062-af28498aa5bb https://jam.dev/c/e61f95ff-f93e-4b74-a3a2-9e2e4dafb175 | closed | *
8 | No option to edit text in headers ,footers or any others except text block | User should be able to edit all types of text content in the page — including headers, footers, and other text elements — not just those placed inside a dedicated text block. | Only text inside a standard "Text Block" is editable. Headers, footers, and other predefined text sections are locked and cannot be edited by the user. | https://www.screenpresso.com/=4CJ5mIspZGfK | closed
9 | No option to edit body section from template screen | User should be able to edit the body section of a template directly from the template screen — including layout, text, images, or dynamic components. | The body section appears locked or non-editable when accessing the template screen. No tools or options are provided to modify its content. | https://www.screenpresso.com/=SOWDI2SKaqHN | closed
10 | [Templates & Pages] Linked Page Does Not Reflect Edited Template Fields in Preview and Lacks Page Field Editing Option | After editing fields in the template, any linked pages should reflect those template updates when previewed. The page should also provide an option to edit its own specific fields (e.g., title, body, metadata) independently, if needed. | When previewing a page linked to a template, the page displays the original template without showing the edited template fields. The page screen does not provide any field editing options, preventing customization or corrections. | https://www.screenpresso.com/=p7c7s2hGtC1g | closed
11 | Non stop loading in filter screen for code field | When accessing the filter screen, the Code field dropdown should load available options once and become selectable within a few seconds. The loading indicator should stop after the data is fetched successfully. | The Code field remains in a continuous loading state, and the dropdown options never appear. Users cannot select any code from the filter due to the loading loop. | https://www.screenpresso.com/=8eCSI6mYzirj | closed
12 | No need to clear button and no action happened when click on | The "Clear" button should either: Be removed if not needed, or Properly clear all applied filters when clicked. | The "Clear" button currently has no effect when clicked. It does not reset or clear any filter fields, making it redundant or misleading for users. | https://www.screenpresso.com/=9O0H1ugrbMDX | closed
13 | bad behaviour when navigate between tabs to choose video and no option to select | User should be able to navigate smoothly between tabs when choosing a video. A clear selection option (e.g., checkbox, select button) should be available for the user to pick a video. | Navigating between video tabs results in unexpected or inconsistent behavior. There is no visible option to select a video, preventing the completion of the action. | https://www.screenpresso.com/=AistmnzMIYJw | closed | * | The select tab is added to images only, but it is still not available in videos, and images are not shown either in preview https://jam.dev/c/6fc4c63f-cdc0-4cbb-9ef9-9c83aaec5f91
14 | No option to add custom image in pages | Users should be able to upload or insert a custom image into the content of a page while creating or editing it. | There is no available option or button in the page editor to add a custom image, limiting the ability to visually enhance or customize content. | https://www.screenpresso.com/=JFhtApGAcaLi | closed
15 | need to give more details for theme screen sub titles |  |  | https://www.screenpresso.com/=cFvtAnCpRzBT | closed | *
16 | No change happened when preview after change color theme of site | The site preview should immediately reflect the new color theme changes, showing updated colors across the site elements. | No change is visible in the site preview; the color theme remains the same as before the update. | https://www.screenpresso.com/=g3YXWme6sTmX | open | Discussion