## الورقة1
THE WEBSITE
BUG NUMBER | Type | BUG TITLE | STEPS FOR REPREDUCE | EXPECTED RESULT | ACTUAL RESULT | VISUAL PROOF OF BUG | SEVERITY | DATE | STATE OF BUG | new date | updates | version | updates 4/11 | comment (dev)
1 | Functional | 404 Home Not Found "home dashboard, employee-performance, company-performance, analytics" | 1-OPEN http://employee-manager.ukkera.com 2-observe the home dashboard | The pages should load with the correct content | A 404 Not Found error is displayed. | https://jam.dev/c/227afb97-2b80-414f-9626-c44668914ebb | High | 14/5 | opening
2 | Functional | Unclear Data Displayed on Translation Page | 1-OPEN http://employee-manager.ukkera.com 2-click on translation 3-Observe the translation results displayed on the page. | All translations should be clear, accurate | Some translation entries show "N/A" | https://jam.dev/c/5e86e11c-022d-4d0b-bd9d-b4a1bcc02120 | Medium | 14/5 | opening
3 | visual | Uploaded photos not displaying properly – showing "server file" placeholder | 1-OPEN http://employee-manager.ukkera.com 2-click on companey 3-click on create and upload the photos 4-observe the photos after uploaded | The uploaded image should be displayed correctly in the UI. | The image is not shown. Instead, a placeholder or the text "server file" appears. | https://jam.dev/c/33825fc7-21f4-4c87-a5c7-f012e5b86cc1 | Medium | 14/5 | opening
4 | Functional | Save Button Not Functioning Properly | 1-OPEN http://employee-manager.ukkera.com 2-navigate to companey 3-click on create and full the requirements 4-click on save and observe | The entered data should be saved and appear in the home page | No data appears in the main page | https://jam.dev/c/a9cdf39b-3092-49c0-ba48-e0c2ee9ddde8 | High | 14/5 | opening
5 | Functional | Missing "Create" Button on Page "attend""skill track""level track""request" | 1-OPEN http://employee-manager.ukkera.com 2-navigate to "attend" and observe | There should be a visible "Create" button on the page that allows users to initiate the creation process. | The "Create" button is not present on the page. | https://jam.dev/c/805edff3-1fd4-4bc3-a6e4-d9a48b2a3c25 | High | 14/5 | opening
6 | Functional | Search Bar Not Visible / Missing from Interface"company,department, attend,skills,skill approval,skill track,project,space,space employee ,category" | 1-OPEN http://employee-manager.ukkera.com 2-navigate to all the pages 3-observe the search bar | The search bar should be visible and accessible to allow users to input search queries. | The search bar is missing from the UI and users cannot perform any search actions. | https://jam.dev/c/fbcca928-b27e-4709-ab71-96a15d684988 | High | 14/5 | opening
7 | content | "Change Language" button does not perform its intended functionality | 1-OPEN http://employee-manager.ukkera.com 2-click on the other language | The application should reload or update the UI to reflect the newly selected language immediately after clicking the "Change Language" button. | No change occurs when the button is clicked The interface remains in the original language. | https://jam.dev/c/dec2d6c2-14af-4408-a29f-628efdf42175 | High | 14/5 | opening
8 | Type | [5 empty] | SEVERITY
| Type | [5 empty] | SEVERITY
| Type | [5 empty] | SEVERITY
| Type | [5 empty] | SEVERITY
| Type | [5 empty] | SEVERITY
| Type | [5 empty] | SEVERITY
| Type | [5 empty] | SEVERITY
| Type |  | THE "HR MANAGER"APP |  |  |  | SEVERITY
1 | Functional | Missing "Create" Button on the screen of "attend track,skill track" | 1-open the app 2-navigate the the screens and observe | There should be a visible "Create" button on the page that allows users to initiate the creation process. | The "Create" button is not present on the page. | https://go.screenpal.com/watch/cTh20CnQ9Rg | High | 14/5 | opening
2 | Functional | Unclear Data Displayed on Translation Page | 1-open the app 2-navigate to the left of the screen and click on translation | All translations should be clear, accurate | Some translation entries show "N/A" | https://go.screenpal.com/watch/cTh20MnQ9Wf | High | 14/5 | opening
3 | content | "Change Language" button does not perform its intended functionality | 1-open the app 2-navigate to the left of the screen and click on change language | The application should reload or update the UI to reflect the newly selected language immediately after clicking the "Change Language" button. | No change occurs when the button is clicked The interface remains in the original language. | https://go.screenpal.com/watch/cTh20PnQ9W7 | High | 14/5 | opening
| Type | [5 empty] | SEVERITY
| Type | [5 empty] | SEVERITY
| Type | [5 empty] | SEVERITY
| Type | [5 empty] | SEVERITY
| Type | [5 empty] | SEVERITY
| Type |  | THE "HR employee"APP |  |  |  | SEVERITY
1 | Functional | "Save" Button is Unclickable in skill approvel | 1-open the app 2-navigate to skill approvel and click on create 3-full the requirements and click on save and observe | The Save button should be clickable and should save the data when clicked. | The Save button does not trigger any action. | https://go.screenpal.com/watch/cThocinQRVw | High | 14/5 | opening
2 | Functional | Unclear Data Displayed on Translation Page | 1-open the app 2-navigate to the left of the screen and click on translation | All translations should be clear, accurate | Some translation entries show "N/A" | https://go.screenpal.com/watch/cThoclnQRni | High | 14/5 | opening
3 | content | "Change Language" button does not perform its intended functionality | 1-open the app 2-navigate to the left of the screen and click on change language | The application should reload or update the UI to reflect the newly selected language immediately after clicking the "Change Language" button. | No change occurs when the button is clicked The interface remains in the original language. | https://go.screenpal.com/watch/cThoc2nQRnT | High | 14/5 | opening
4 | Functional | Screen displays "not found module" and no data appears in "projects""work space" | 1-open the app 2-navigate to the "projects""work space" | The screen should load and display the relevant data or components. | No data is shown. Instead, the message "not found module" is displayed. | https://go.screenpal.com/watch/cThocrnQRew | High | 14/5 | opening
Type
Type